## Sheet1
Task ID | Task Name | Phase | Start Date | End Date | Duration (days) | Assigned To | Status
1 | Project Initiation | Initiation Phase | 2025-07-01 | 2025-07-03 | 3 | Project Manager | Completed
2 | Requirement Gathering | Planning Phase | 2025-07-04 | 2025-07-07 | 4 | Business Analyst | Completed
3 | Create SRS Document | Planning Phase | 2025-07-08 | 2025-07-10 | 3 | BA, Tech Lead | Completed
4 | Create WBS | Planning Phase | 2025-07-11 | 2025-07-12 | 2 | PMO | Completed
5 | UI/UX Design | Design Phase | 2025-07-13 | 2025-07-17 | 5 | Designer | In Progress
6 | Backend Architecture Setup | Design Phase | 2025-07-13 | 2025-07-16 | 4 | Tech Lead | In Progress
7 | Database Design | Design Phase | 2025-07-14 | 2025-07-18 | 5 | Database Developer | In Progress
8 | Frontend Development | Development Phase | 2025-07-18 | 2025-07-26 | 9 | Frontend Dev Team | Not Started
9 | Backend Development | Development Phase | 2025-07-18 | 2025-07-28 | 11 | Backend Dev Team | Not Started
10 | API Integration | Development Phase | 2025-07-27 | 2025-07-30 | 4 | Full Stack Dev | Not Started
11 | Testing (Unit + Integration) | Testing Phase | 2025-07-30 | 2025-08-03 | 5 | QA Team | Not Started
12 | UAT and Bug Fixes | Testing Phase | 2025-08-04 | 2025-08-06 | 3 | QA & Dev Team | Not Started
13 | Final Deployment | Deployment Phase | 2025-08-07 | 2025-08-07 | 1 | DevOps Team | Not Started
14 | Project Closure Report | Closure Phase | 2025-08-08 | 2025-08-08 | 1 | Project Manager | Not Started