## Sheet1
Communication Type | Purpose | Frequency | Participants | Medium / Tool | Owner
Kick-off Meeting | Project Initiation | Once | Project Manager, Team Leads | Zoom / MS Teams | Project Manager
Weekly Status Meeting | Progress Review | Weekly (Monday) | Core Team, PM | Google Meet / Teams | Project Manager
Sprint Review | Showcase deliverables | Bi-weekly | Dev Team, Stakeholders | Zoom | Scrum Master / PM
Risk Review Meeting | Identify/Mitigate Risks | Bi-weekly | QA, Dev Leads, PM | Teams / Email Summary | Risk Manager / PM
Stakeholder Report | High-level progress update | Monthly | Stakeholders | Email (PDF Attachment) | Project Coordinator
Final Project Review | Closure & Lessons Learned | End of project | All stakeholders | In-person / Online Meet | Project Manager